## About
(no number) KCGM Growth Work Breakdown Structure
Tables only, from the original PDF (Every data table in the PDF (cover page and sign off tables left out), one sheet each). Cover page, logos, sign off names and file metadata removed. Built by tools/build_sources.py.
Sheet | Rows | Columns | Hidden in the original
p1 t1 | 6 | 2
p1 t2 | 63 | 2
p1 t3 | 108 | 2
p1 t4 | 13 | 2
p1 t5 | 105 | 2
p1 t6 | 106 | 2
p1 t7 | 77 | 2
p1 t8 | 44 | 2

## p1 t1
WBS Level 1 - Major Facility
M | Mining
F | Fimiston Processing
T | Tailings Facility
N | Non-Process Infrastructure (NPI)
P | Indirects (Owner's)

## p1 t2
Code | Description
M00 | Mining
M00 010 | Mining - General
M01 | Exploration - Capitalized
M01 010 | General - Exploration
M02 | Open Pit Mining / Geology
M02 010 | General - Aboveground Mining / Geology
M02 020 | Facilities / Infrastructure - Other
M02 030 | Facilities / Infrastructure - A/G Support
M02 040 | Facilities / Infrastructure - Explosive Storage
M02 050 | Facilities / Infrastructure - Fuel Storage
M02 060 | Facilities / Infrastructure - Mine Water Treatment
M02 070 | Resource Development / Sterilization Drilling
M02 080 | Topsoil Storage
M02 090 | Waste Dump
M02 100 | LOM Stockpile
M02 110 | Unsuitable Waste
M02 120 | Pre-strip
M02 130 | Haul Roads
M02 140 | Pit Dewatering
M02 150 | A/G Fleet / Equipment
M02 160 | Grade Control
M02 170 | Site Services - Other
M02 180 | Site Services - Power Generation / Distribution
M02 190 | Site Services - Water / Air Supply & Distribution
M02 200 | Site Services - Fuel/Lubes Dispensing
M02 210 | Facilities / Infrastructure - Mine Buildings
M02 220 | Mining Information Systems
M03 | Underground Mining / Geology
M03 010 | General
M03 020 | Facilities / Infrastructure - Other
M03 030 | Facilities / Infrastructure - U/G Support
M03 040 | Facilities / Infrastructure - Explosive Storage
M03 050 | Facilities / Infrastructure - Fuel Storage
M03 060 | Facilities / Infrastructure - Mine Water Treatment
M03 070 | Facilities / Infrastructure - Paste / Backfill
M03 080 | Boxcut / Portal
M03 090 | Decline
M03 100 | Well Point System
M03 110 | Level Development - Horizontal Development
M03 120 | Production Shaft - Vertical Development
M03 130 | Production Shaft - Sub Collar
M03 140 | Production Shaft - Collar & Headframe
M03 150 | Production Shaft - Hoisting
M03 160 | Ore & Waste handling (passes & raises)-Vertical Development
M03 170 | Ore / Waste Raises - Sub Collar
M03 180 | Ore / Waste Raises - Collar & Headframe
M03 190 | Ore / Waste Raises - Hoisting
M03 200 | Ore / Waste passes
M03 210 | Ventilation Shaft - Vertical Development
M03 220 | Ventilation Shaft - Sub Collar
M03 230 | Ventilation Shaft - Collar & Headframe
M03 240 | Ventilation Shaft - Hoisting
M03 250 | Ventilation Shaft - Mine Air Tempering
M03 260 | Vent Raises
M03 270 | U/G Fleet / Equipment
M03 280 | Site Services - Other
M03 290 | Site Services - Power Generation / Distribution
M03 300 | Site Services - Water / Air Supply & Distribution
M03 310 | Site Services - Ventilation Distribution
M03 320 | Site Services - Dewatering
M03 330 | Site Services - Fuel/Lubes Dispensing
M03 340 | Ore Stockpile (Surface)

## p1 t3
Code | Description
F00 | General Fimiston Site
F00 010 | General Fimiston Site - General
F00 020 | HV Power Distribution
F00 030 | Buried Services
F00 040 | Piperacks
F00 050 | LV Power Distribution
F10 | Primary Crushing - Existing
F10 010 | <spare - not used>
F10 020 | <spare - not used>
F10 030 | <spare - not used>
F12 | Primary Crushing
F12 010 | Primary Crushing - General
F12 020 | Crushed Ore Stockpile
F12 030 | Conveyors
F13 | Milling & Classification
F13 010 | Milling & Classification - General
F13 020 | Stockpile Reclaim
F13 030 | Milling
F13 040 | Pebble Crushing
F13 050 | Trash Screens
F13 060 | Conveyors
F14 | Gravity Circuit & Intensive Leaching
F14 010 | Gravity Circuit & Intensive Leaching - General
F14 020 | Gravity Circuit & Intensive Leaching
F16 | Rougher & Scavenger Flotation
F16 010 | Rougher & Scavenger Flotation - General
F16 020 | Rougher & Scavenger Flotation
F17 | Flotation Tailings Pre-Leach Thickening
F17 010 | Flotation Tailings Pre-Leach Thickening - General
F17 020 | Flotation Tailings Pre-Leach Thickening
F18 | Cleaner & Cleaner Scavenger Flotation
F18 010 | Cleaner & Cleaner Scavenger Flotation - General
F18 020 | Cleaner & Cleaner Scavenger Flotation
F19 | Milling & Classification - Fimiston Existing - Area A
F19 010 | Milling & Classification - Fimiston Existing - Area A - General
F19 020 | Regrind Mill (Repurpose)
F20 | Milling & Classification - Area B
F20 010 | General
F20 020 | Flotation
F20 030 | Leach & Recovery
F21 | Flotation Tailings CIL4
F21 010 | Flotation Tailings CIL4 - General
F21 020 | CIL4 Train A
F21 030 | CIL4 Train B
F21 040 | CIL4 Carbon Safety Screens
F22 | CIL4 - Carbon Treatment & Elution
F22 010 | CIL4 - Carbon Treatment & Elution - General
F22 020 | CIL4A Elution
F22 030 | CIL4B Elution
F22 040 | CIL4 Carbon Regeneration
F22 050 | CIL4 Carbon Regeneration Off Gas Treatment
F23 | Final Tailings Handling & Storage
F23 010 | Final Tailings Handling & Storage - General
F23 020 | Final Tails Pumps
F23 030 | Final Tails Booster Pumps
F23 040 | Tailings Storage Distribution
F24 | Air & Water Services
F24 010 | Air & Water Services - General
F24 020 | Process Water
F24 030 | Gland Water
F24 040 | Raw Water
F24 050 | Saline Water
F24 060 | Plant Air
F24 070 | Instrument Air
F28 | Ultra Fine Grinding 2 / 3
F28 010 | Ultra Fine Grinding 2 / 3 - General
F28 020 | Ultra Fine Grinding 2 / 3
F30 | Concentrate Pre-Leach Thickening, CIL2/3 & Concentrate Thickening
F30 010 | Conc Pre-Leach Thickening, CIL2/3 & Conc Thickening - General
F30 020 | Concentrate Pre-Leach Thickening
F30 030 | CIL2/3
f30 040 | Post-Leach Thickening
F34 | Ultra Fine Grinding - Existing
F34 010 | Ultra Fine Grinding - Existing - General
F34 020 | UFG Mill Product
F35 | Concentrate Handling & Filtration
F35 010 | Concentrate Handling & Filtration - General
F35 020 | Concentrate Handling & Filtration
F35 030 | Conveyors
F65 | Concentrate Carbon Treatment & Elution
F65 010 | Concentrate Carbon Treatment & Elution - General
F66 | Electrowinning & Goldroom
F66 010 | Electrowinning & Goldroom - General
F66 020 | CIL4A/4B Electrowinning
F66 030 | Gravity Electrowinning
F72 | Reagents Mixing & Storage
F72 010 | Reagents Mixing & Storage - General
F72 020 | PAX
F72 030 | Frother
F72 040 | Copper Sulphate
F72 050 | Oxygen
F72 060 | Caustic
F72 070 | Acid
F72 080 | Cyanide
F72 090 | Lead Nitrate
F72 100 | LNG
F72 110 | Lime
F72 120 | Flocculant
F75 | Water Services - Existing
F75 010 | <spare - not used>
F75 020 | <spare - not used>
F78 | Carbon Regeneration - Existing
F78 010 | <spare - not used>
F78 020 | <spare - not used>
F81 | Air Services - Existing
F81 010 | <spare - not used>
F81 020 | <spare - not used>

## p1 t4
Code | Description
T00 | Tailings Management
T00 010 | Tailings Management - General
T03 | Fim III Tailings Storage Facility (TSF)
T03 010 | Fim III Tailings Storage Facility - General
T03 020 | Site Development
T03 030 | Tailings Pipeline
T03 040 | Fim III TSF (Initial Capital)
T03 050 | Impoundment
T03 060 | Tailings Distribution System
T03 070 | Fim III TSF (Sustaining Capital)
T03 080 | Return Water System / Pumping
T03 090 | Return Water Pipeline

## p1 t5
Code | Description
P00 | Indirects (Owner's)
P00 010 | Indirects (Owner's) - General
P10 | Site Construction Expenses
P11 | Temporary Construction Facilities
P11 010 | Temporary Construction Facilities - General
P11 020 | Temporary Construction Buildings
P11 030 | Temporary Utilities - Power
P11 040 | Temporary Utilities - Water, Sewer & Trash
P11 050 | Temporary Utilities - Communication
P11 060 | Catering, Janitorial
P11 070 | Temporary Warehouse Facilities
P11 080 | Temporary Weather Protection
P11 090 | Batch Plant
P12 | Temporary Site Development
P12 010 | Temporary Site Development - General
P12 020 | Mobilization
P12 030 | De-Mobilization
P12 040 | Laydown/Fabrication Areas
P12 050 | Parking
P12 060 | Gate/Brass Alley
P12 070 | Fencing
P12 080 | Temporary Roads
P12 090 | Security
P13 | Construction Equipment, Tools, Supplies
P13 010 | Construction Equipment, Tools, Supplies - General
P13 020 | Construction Equipment - Cranes
P13 030 | Construction Equipment - Mobile Equipment
P13 040 | Construction Equipment - Other
P13 050 | Tools & Consumables
P13 060 | Safety Supplies & Equipment
P13 070 | Scaffolding
P13 080 | Fuel
P14 | Construction Support
P14 010 | Construction Support - General
P14 020 | Training & Skill Improvement
P14 030 | Bussing
P15 | Construction Project Expenses
P15 010 | Construction Project Expenses - General
P15 020 | Sealift
P20 | Insurance, Taxes/Levies, Bonds, License Fees, Royalties, Currency Hedgi
P20 010 | Insurance
P20 020 | Taxes
P20 030 | Bonds
P20 040 | License Fees
P20 050 | Royalties
P20 060 | Currency Hedging
P20 070 | FOREX
P20 080 | Permits
P20 090 | Bank Fees
P30 | EPC/EPCM Cost
P31 | EPC/EPCM Cost - General
P31 010 | EPC/EPCM Cost - General
P31 020 | Engineering & Design Cost
P31 030 | Construction Management Cost
P31 040 | Project Management Cost
P31 050 | Fee - E / EP / EPC / EPCM
P32 | EPC/EPCM Construction Support
P32 010 | EPC/EPCM Construction Support
P32 020 | Office Supplies & Expenses
P32 030 | Site Vehicles & Transportation
P33 | Project Standby - Construction/CM
P33 010 | Standby - Construction
P33 020 | Standby - Construction Management Services
P33 030 | Standby - CM-Contractors
P40 | Third Party Consultants
P41 | Third Party Consultants - Engineering
P41 010 | Third Party Consultants - Engineering
P41 020 | Geotechnical
P41 030 | Engineering Services
P42 | Third Party Consultants - Site
P42 010 | Third Party Consultants - Site
P42 020 | Geotechnical
P42 030 | Environmental
P50 | Freight & Duties
P50 010 | Freight & Duties
P60 | Other Project Cost
P61 | Pre-Commissioning/Commissioning
P61 010 | Pre-Commissioning/Commissioning (Craft Support) - General
P61 020 | Pre-Commissioning (Craft Support)
P61 030 | Commissioning (Craft Support)
P62 | Vendor Representatives
P62 010 | Vendor Representatives
P63 | Spares / First Fills
P63 010 | Spares / First Fills - General
P63 020 | Spares
P63 030 | First Fills
P64 | Escalation
P64 010 | Escalation
P65 | Contingency
P65 010 | Contingency
P70 | Owner's Project Services
P71 | Exploration
P71 010 | Exploration - General
P71 020 | Exploration - Generative Exploration
P71 030 | Exploration - Near Mine
P72 | Geology
P72 010 | Geology - General
P72 020 | Geology - Site Investigation
P72 030 | Mine Geology - Sterilization Drilling
P72 040 | Mine Geology - Infill Drilling
P72 050 | Mine Geology - Metallurgy Drilling
P72 060 | Geology - Studies
P73 | Resource Estimation
P73 010 | Resource Estimation - General

## p1 t6
Code | Description
P74 | Mine Engineering
P74 010 | Mine Engineering - General
P74 020 | Mine Engineering - Above Ground
P74 030 | Mine Engineering - Under Ground
P75 | Metallurgy
P75 010 | Metallurgy - General
P75 020 | Metallurgy - Testing
P76 | Project Support
P76 010 | Project Mgt & Administration - General
P76 020 | Business Management
P76 030 | Administrative Staff
P76 040 | Information Technology (IT)
P76 050 | HSLP
P76 060 | Security
P76 070 | Communications
P76 080 | Document Control
P76 090 | Office Management
P77 | Project Services
P77 010 | Project Services - General
P77 020 | Project Management
P77 030 | Project Engineering
P77 040 | Project Business Analysis
P77 050 | Project Controls
P77 060 | Project Supply Chain Management (SCM)
P77 070 | Project Commercial
P77 080 | Project Accounting
P77 090 | Project Estimation/Benchmarking
P77 100 | <spare - not used>
P78 | Corporate Services
P78 010 | Corporate Services - General
P78 020 | Land & Concessions
P78 030 | Legal
P78 040 | Finance/Accounting
P78 050 | Business Planning
P78 060 | Global Risk Management
P78 070 | Tax
P78 080 | Treasury
P78 090 | Business Readiness
P78 100 | Human Resources (HR)
P79 | Environmental & Social Responsibility (ESR)
P79 010 | ESR - General
P79 020 | ESR - EIA/EIS Support
P79 030 | ESR - Studies
P80 | Intercompany Charges
P80 010 | Intercompany - General
P80 020 | Intercompany - TS Projects
P80 030 | Intercompany - TS Mining
P80 040 | Intercompany - Metallurgical Services
P80 050 | Intercompany - TS Other
P91 | Owner's Mine Operataions and Maintenance Construction Support
P91 010 | Mine Ops Services - General
P91 020 | Mine Planning
P91 030 | Mine Engineering
P91 040 | Mine Survey
P91 050 | Mine Project Development
P91 060 | Mine Operations
P91 070 | Mine Maintenance
P91 080 | Mine Water Management
P91 090 | Mine Process
P91 100 | Mine QA\QC
P91 110 | Mine ESR - General
P91 120 | Mine ESR EA - Social Development & Mitigation
P91 130 | Mine ESR EA - Community Relations
P91 140 | Mine ESR EA - Govt & Inst Relationships & Comm
P91 150 | Mine ESR EA - Planning & Monitoring
P91 160 | Mine ESR - Permitting
P91 170 | Mine ESR - Environmental
P92 | Owner's Site Expenses
P92 010 | Owner's Expenses - General
P92 020 | Light Vehicles
P92 030 | Project Completion Bonus
P92 040 | Workers Participation
P92 050 | Charter Flights
P92 060 | Project Standby - Owner (General)
P92 070 | Storage & Preservation
P93 | Land Access & Resettlement
P93 010 | Land Access & Resettlement
P93 020 | Resettlement Construction
P93 030 | Land Access Compensation (Cash Payments,livehood, etc)
P93 040 | Land Access Consultants
P93 050 | Water Rights Compensation
P94 | Owner's Commissioning
P94 010 | Owner's Commissioning
P95 | Owner's Pre-Production Ramp-Up Cost
P95 010 | Owner's Pre-Production Ramp-Up
P95 020 | Owner's Pre-Production Ramp-Up - Cost
P95 030 | Owner's Pre-Production Ramp-Up - Revenue
P96 | Owner's Hedging Gain/Loss / FOREX
P96 010 | Notational Hedging Gain / Loss
P91 020 | FOREX
P97 | Owner's Capitalized Interest
P97 010 | Capitalized Interest
P98 | Owner's Escalation & Unallocated Cost
P98 010 | Unallocated Project Cost
P98 020 | Owner's Escalation
P98 030 | Sustaining Capital
P99 | Owner's Contingency / Reserve
P99 010 | Owner's Contingency
P99 020 | Owner's Reserve
P99 030 | Project Director's Reserve
P99 040 | Special Reserve
P99 050 | Owner SOW - Reserve
P99 060 | EPCM SOW - Reserve
P99 070 | Event Contingency
P99 080 | Market Condition

## p1 t7
WBS Level 2 - Sub-Facility
M00 | Mining
M01 | Exploration - Capitalized
M02 | Open Pit Mining / Geology
M03 | Underground Mining / Geology
F00 | General Fimiston Site
F10 | Primary Crushing - Existing
F12 | Primary Crushing
F13 | Milling & Classification
F14 | Gravity Circuit & Intensive Leaching
F16 | Rougher & Scavenger Flotation
F17 | Flotation Tailings Pre-Leach Thickening
F18 | Cleaner & Cleaner Scavenger Flotation
F19 | Milling & Classification - Fimiston Existing - Area A
F20 | Milling & Classification - Area B
F21 | Flotation Tailings CIL4
F22 | CIL4 - Carbon Treatment & Elution
F23 | Final Tailings Handling & Storage
F24 | Air & Water Services
F28 | Ultra Fine Grinding 2 / 3
F30 | Concentrate Pre-Leach Thickening, CIL2/3 & Concentrate Thickening
F34 | Ultra Fine Grinding - Existing
F35 | Concentrate Handling & Filtration
F65 | Concentrate Carbon Treatment & Elution
F66 | Electrowinning & Goldroom
F72 | Reagents Mixing & Storage
F75 | Water Services - Existing
F78 | Carbon Regeneration - Existing
F81 | Air Services - Existing
T00 | Tailings Management
T03 | Fim III Tailings Storage Facility (TSF)
N00 | Non-Process Infrastructure (NPI)
N02 | Kaltails Borefields
N03 | On-Site Infrastructure - Plant
N04 | Off-Site Infrastructure - Excludes Plant & Mine
P00 | Indirects (Owner's)
P10 | Site Construction Expenses
P11 | Temporary Construction Facilities
P12 | Temporary Site Development
P13 | Construction Equipment, Tools, Supplies
P14 | Construction Support
P15 | Construction Project Expenses
P20 | Insurance, Taxes/Levies, Bonds, License Fees, Royalties, Currency Hedgi
P30 | EPC/EPCM Cost
P31 | EPC/EPCM Cost - General
P32 | EPC/EPCM Construction Support
P33 | Project Standby - Construction/CM
P40 | Third Party Consultants
P41 | Third Party Consultants - Engineering
P42 | Third Party Consultants - Site
P50 | Freight & Duties
P60 | Other Project Cost
P61 | Pre-Commissioning/Commissioning
P62 | Vendor Representatives
P63 | Spares / First Fills
P64 | Escalation
P65 | Contingency
P70 | Owner's Project Services
P71 | Exploration
P72 | Geology
P73 | Resource Estimation
P74 | Mine Engineering
P75 | Metallurgy
P76 | Project Support
P77 | Project Services
P78 | Corporate Services
P79 | Environmental & Social Responsibility (ESR)
P80 | Intercompany Charges
P91 | Owner's Mine Operataions and Maintenance Construction Support
P92 | Owner's Site Expenses
P93 | Land Access & Resettlement
P94 | Owner's Commissioning
P95 | Owner's Pre-Production Ramp-Up Cost
P96 | Owner's Hedging Gain/Loss / FOREX
P97 | Owner's Capitalized Interest
P98 | Owner's Escalation & Unallocated Cost
P99 | Owner's Contingency / Reserve

## p1 t8
Code | Description
N00 | Non-Process Infrastructures (NPI)
N00 010 | NPI - General
N02 | Kaltails Borefields
N02 010 | Pump Station
N02 020 | Pipeline
N02 030 | Environmental Control Structure
N02 040 | Diversion Channel
N02 050 | Dyke
N02 060 | RO System / Acid Water Treatment
N02 070 | Water Wells
N03 | On-Site Infrastructure - Plant & Mine
N03 010 | On-Site Infrastructure - Plant - General
N03 020 | Site Development
N03 030 | Plant Roads
N03 040 | Data and Communications
N03 050 | Process Control System
N03 060 | Equipment (Mobile, Utility, Misc)
N03 070 | ESS Workshop
N03 080 | Cribs & Ablution
N03 090 | Operation Readiness & Training Room Building
N03 100 | Black Street Office
N03 110 | Main Control Building
N03 120 | Mining Office
N03 130 | HV Workshop & Warehouse
N03 140 | HV Tyre Change
N03 150 | Core Shed
N03 160 | Hall of Fame (Hannen)
N03 170 | <spare - not used>
N03 180 | <spare - not used>
N04 | Off-Site Infrastructure - Excludes Plant & Mine
N04 010 | Off-Site Infrastructure - General
N04 020 | Site Development
N04 030 | Roads - Permanent
N04 040 | Data and Communications
N04 050 | Process Control System
N04 060 | Equipment (Mobile, Utility, Misc)
N04 070 | Earthmoving Equipment
N04 080 | Township
N04 090 | Landfill Facility
N04 100 | Camp
N04 110 | <spare - not used>
N04 120 | <spare - not used>
N04 130 | <spare - not used>